## Projects
Type | Company Name | Owner Name | Project Title | Project ID | Short Name | Market Sector | Project Type | Service Type | Category | Business Unit | Division | Department | Status | Start Date | End Date | Actual Start | Actual End | Construction Start | Substantial Completion | Closeout Date | Contract Value | Labor Budget | Gross Margin | Contract Type | Contracted Amount | Proposal Amount | Bid Amount | Change Orders | Approved Change Orders | Retainage | Fee % | Contingency | Total Project Cost | % Complete | Priority | Next Milestone | Next Milestone Date | Description | Project Summary Note | Comments | Contract Notes | Street Address | City | State
Project | Metro Transit Authority | J. Carter | Downtown Rail Extension — Phase 2 | JOB-2024-0412 | Rail-Ph2 | Transportation | Infrastructure | Engineering | Heavy Rail | Civil & Transit | Infrastructure | Rail | Active | 2024-03-01 | 2026-09-30 | 2024-03-01 |  | 2024-06-01 | 2026-08-31 |  | 48500000 | 18000000 | 9700000 | GMP | 48500000 | 50000000 | 47800000 | 1200000 | 900000 | 2425000 | 8 | 2400000 | 51125000 | 35 | High | Structure Pour | 2025-08-15 | Downtown rail corridor phase 2 extension | Phased delivery, high complexity urban corridor | On schedule per last review | GMP contract includes $2.4M contingency | 400 Rail Blvd | Metro City | CA
Project | City General Hospital | A. Patel | Surgical Wing Expansion | JOB-2024-0530 | SurgWing | Healthcare | Healthcare | Architecture | Medical | Healthcare Studio | Healthcare | Design | Active | 2024-06-15 | 2025-12-31 | 2024-06-15 |  | 2024-09-01 | 2025-11-30 |  | 22750000 | 8500000 | 4550000 | Fixed | 22750000 | 23500000 | 22400000 | 350000 | 350000 | 1137500 | 6 | 1137000 | 23887500 | 20 | High | MEP Rough-In | 2025-03-20 | New surgical wing with 8 OR suites | Infection-control critical path | Procurement lead time flagged for OR equipment | Fixed-fee with owner-supplied equipment allowance | 150 Hospital Ave | Riverside | CA
Project | Riverside Municipality | D. Nguyen | Riverside Civic Centre Renovation | JOB-2023-1104 | CivicReno | Government | Civic | Construction Mgmt | Public Facility | Civic & Culture | Government | Civic | On Hold | 2024-01-10 | 2025-06-30 | [5 empty] | 9200000 | 3400000 | 1840000 | T&M | 9200000 | 9800000 | 9050000 | 0 | 0 | 460000 | 7 | 460000 | 9660000 | 10 | Medium | Design Approval | 2024-11-01 | Heritage-listed civic centre full renovation | On hold pending council heritage approval | Awaiting heritage impact statement sign-off | T&M capped at $9.2M | 200 Civic Plaza | Riverside | CA
Project | Harborview Development LLC | R. Stone | Harborview Mixed-Use Tower | JOB-2025-0210 | HarborTwr | Real Estate | Commercial | Design-Build | Mixed-Use | Commercial RE | Commercial | Development | Active | 2023-11-01 | 2026-03-31 | 2023-11-01 |  | 2024-02-01 | 2026-01-31 |  | 134000000 | 50000000 | 26800000 | GMP | 134000000 | 138000000 | 131500000 | 4200000 | 3800000 | 6700000 | 9 | 6700000 | 140700000 | 55 | High | Podium Topping Out | 2025-11-01 | 45-storey mixed-use residential & retail tower | Tallest private development in the Harborview precinct | Crane agreement with adjacent site executed | GMP includes $6.7M contingency buffer | 1 Harbor St | Harbor City | CA
Project | NexGen Cloud Corp | S. Kim | Tier-4 Data Centre Build | JOB-2025-0315 | DC-T4 | Technology | Mission Critical | Engineering | Data Centre | Technology | Commercial | Mission Crit | Pending | 2025-01-15 | 2026-08-31 |  |  | 2025-04-01 | 2026-07-31 |  | 67300000 | 25000000 | 13460000 | GMP | 67300000 | 69000000 | 66500000 | 0 | 0 | 3365000 | 10 | 3365000 | 70665000 | 0 | High | Design Review | 2025-01-30 | Tier-4 certified hyperscale data centre campus | Critical uptime SLA of 99.9995% | Mechanical vendor shortlisted | GMP pending owner sign-off | 500 Innovation Dr | Tech Park | CA
Project | State DOT | L. Martinez | Highway 9 Bridge Replacement | JOB-2024-0981 | HWY9-Br | Transportation | Infrastructure | Engineering | Bridge | Civil & Transit | Infrastructure | Bridges | Active | 2024-09-01 | 2027-04-30 | 2024-09-01 |  | 2025-01-15 | 2027-02-28 |  | 31800000 | 12000000 | 6360000 | Fixed | 31800000 | 32500000 | 31200000 | 640000 | 500000 | 1590000 | 8 | 1590000 | 33390000 | 15 | Medium | Pier Cap Pour | 2026-04-01 | Full replacement of aging Highway 9 river bridge | CALTRANS funded, environmental clearance complete | Rebar delivery on track | Fixed-price with CALTRANS standard escalation clauses | HWY 9 MM 42 | Westfield | CA
Project | Metro Airport Authority | T. Okonkwo | Airport Terminal C Expansion | JOB-2024-0720 | TermC-Exp | Transportation | Aviation | Construction Mgmt | Terminal | Civil & Transit | Infrastructure | Aviation | Active | 2024-07-01 | 2028-06-30 | 2024-07-01 |  | 2025-01-01 | 2028-03-31 |  | 285000000 | 95000000 | 57000000 | GMP | 285000000 | 292000000 | 280000000 | 8500000 | 7200000 | 14250000 | 10 | 14250000 | 299250000 | 8 | Critical | Security Checkpoint Layout Approval | 2025-09-01 | Full expansion of International Terminal C — 22 new gates | Airside works require FAA coordination and night-shift only | Night-shift premium approved by board | Program management services fee included in GMP | 1 Airport Blvd | Metro City | CA
Project | Lakeview School District | M. Chen | K-12 Campus Modernisation | JOB-2025-0088 | K12-Mod | Education | Education | Architecture | K-12 | Civic & Culture | Government | Education | Active | 2025-02-01 | 2027-01-31 | 2025-02-01 |  | 2025-05-01 | 2026-12-31 |  | 17600000 | 6800000 | 3520000 | GMP | 17600000 | 18200000 | 17300000 | 300000 | 300000 | 880000 | 6 | 880000 | 18480000 | 5 | Medium | Structural Steel Award | 2025-07-15 | Full modernisation of 3 school buildings and new gymnasium | DSA approval required before construction start | DSA application submitted Jan 2025 | GMP subject to DSA approval condition | 300 School Rd | Lakeview | CA
Project | Pacific Energy Co | B. Walsh | Solar Array Substation Build | JOB-2025-0441 | Solar-SS | Energy | Energy | Engineering | Substation | Technology | Commercial | Energy | Active | 2025-03-15 | 2026-11-30 | 2025-03-15 |  | 2025-06-01 | 2026-10-31 |  | 54200000 | 19500000 | 10840000 | Fixed | 54200000 | 55800000 | 53500000 | 700000 | 700000 | 2710000 | 9 | 2710000 | 56910000 | 12 | High | Transformer Delivery | 2026-02-01 | Solar substation serving 200MW utility-scale array | Long-lead transformer procurement on critical path | Transformer ordered — 48-week lead time | Fixed-fee, liquidated damages clause applies | 800 Solar Pkwy | Sunnyvale | CA
Project | Grand Hotel Group | F. Romano | Beachfront Hotel & Spa Fitout | JOB-2024-0867 | Hotel-Spa | Hospitality | Hospitality | Design-Build | Hotel Fitout | Commercial RE | Commercial | Interiors | Complete | 2023-08-01 | 2024-12-31 | 2023-08-01 | 2024-12-20 | 2023-10-01 | 2024-11-30 | 2025-01-15 | 12400000 | 4800000 | 2480000 | T&M | 12400000 | 13000000 | 12100000 | 400000 | 400000 | 620000 | 7 | 620000 | 13020000 | 100 | Medium | Final Defects Rectified | 2024-12-01 | Luxury hotel fitout — 180 keys plus destination spa | Delivered on time and under budget | Defects liability period commenced Dec 2024 | T&M with GMP ceiling; final account agreed | 10 Ocean Dr | Beachside | CA

## Team Assignments
Project | Name | Email | Start Date | End Date | Allocation % | Total Hours | Type | Role | Job Title | Business Unit | Division | Department | Billing Rate | Labor Rate | Cost Rate | Actual Start | Actual End | Actual Hours | Billed Hours | Access Level
Downtown Rail Extension — Phase 2 | Sarah Mitchell | s.mitchell@aceco.com | 2024-03-01 | 2026-09-30 | 80 | 3200 | Hard | Senior Engineer | Project Engineer | Civil & Transit | Infrastructure | Rail | 180 | 140 | 110 | 2024-03-01 |  | 2100 | 2000 | editor
Downtown Rail Extension — Phase 2 | Kevin Park | k.park@aceco.com | 2024-03-01 | 2026-09-30 | 100 | 4000 | Hard | Project Manager | Senior PM | Civil & Transit | Infrastructure | Rail | 200 | 155 | 125 | 2024-03-01 |  | 2600 | 2500 | editor
Surgical Wing Expansion | Tom Williams | t.williams@aceco.com | 2024-06-15 | 2025-12-31 | 100 | 3500 | Hard | Project Manager | PM | Healthcare Studio | Healthcare | Design | 200 | 155 | 125 | 2024-06-15 |  | 1800 | 1750 | editor
Harborview Mixed-Use Tower | Chris Lee | c.lee@aceco.com | 2023-11-01 | 2026-03-31 | 80 | 4800 | Hard | Structural Lead | Principal Engineer | Commercial RE | Commercial | Structures | 210 | 165 | 130 | 2023-11-01 |  | 3200 | 3100 | editor
Airport Terminal C Expansion | James Norton | j.norton@aceco.com | 2024-07-01 | 2028-06-30 | 100 | 8000 | Hard | Program Director | Director | Civil & Transit | Infrastructure | Aviation | 250 | 195 | 155 | 2024-07-01 |  | 4500 | 4400 | admin
Highway 9 Bridge Replacement | Priya Sharma | p.sharma@aceco.com | 2024-09-01 | 2027-04-30 | 50 | 3200 | Hard | Project Manager | Senior PM | Civil & Transit | Infrastructure | Bridges | 200 | 155 | 125 | 2024-09-01 |  | 1200 | 1150 | editor
Tier-4 Data Centre Build | Amy Chen | a.chen@aceco.com | 2025-01-15 | 2026-08-31 | 100 | 3600 | Hard | MEP Engineer | Senior Engineer | Technology | Commercial | MEP | 175 | 135 | 108 |  |  | 0 | 0 | editor
K-12 Campus Modernisation | David Okafor | d.okafor@aceco.com | 2025-02-01 | 2027-01-31 | 80 | 3840 | Hard | Project Manager | PM | Civic & Culture | Government | Education | 190 | 148 | 118 | 2025-02-01 |  | 400 | 380 | editor
Solar Array Substation Build | Nina Kowalski | n.kowalski@aceco.com | 2025-03-15 | 2026-11-30 | 100 | 3900 | Hard | Electrical Lead | Principal Engineer | Technology | Commercial | Energy | 195 | 152 | 122 | 2025-03-15 |  | 600 | 580 | editor
Beachfront Hotel & Spa Fitout | Marco Ricci | m.ricci@aceco.com | 2023-08-01 | 2024-12-31 | 60 | 2400 | Hard | Interior Design | Design Lead | Commercial RE | Commercial | Interiors | 165 | 128 | 102 | 2023-08-01 | 2024-12-20 | 2400 | 2400 | editor