## Clients & Projects
Type | Company Name | Contacts | Client Rep | CRM Health | Market Sector | Project Title | Job ID | Project Type | Service Type | Request Category | Category | Project Tag | Contract Value | Approx Value | Contract Limit | Labor Budget | Gross Margin | Contract Type | Status | Chance of Success | Opportunity Stage | Business Unit | Division | Department | Sector | Start Date | End Date | Actual Start | Actual End | Desired Completion | Proposal Due Date | Bid Due Date | Interview Date | Precon Start | Precon End | Construction Start | Est. Constr. Start | Est. Constr. End | Closeout Start | Closeout Date | Closed Date | Primary Contact | Project Lead | Project Manager | Senior Project Manager | Business Lead | Owner | Program Manager | Lead Estimator | Lead Superintendent | Estimator | Project Summary | Next Activity | Next Milestone | Risk Score | Project Rank | Short Name | ─── Team Member ─── | Team Member Email | Member Role | Member Division | Alloc Start | Alloc End | Allocation % | Total Hours | Alloc Type
Project or Opportunity | Client company name (e.g. Metro Transit Authority) | Client contact person(s) — separate multiple with semicolon | Your firm's account owner for this client (optional) | Client relationship health: Good / Fair / Poor | e.g. Construction, Transportation, Healthcare | ★ Project or opportunity name | Your internal job / ERP reference number | e.g. Design, Construction, Consulting, Renovation | e.g. Architecture, Engineering, PM, MEP | Request or work category (optional) | Project category / classification (optional) | Free-text tag or label for this project (optional) | Total contract value in dollars (number only) | Approximate contract value — number only (optional) | Not-to-exceed cap in dollars (number only, optional) | Labor portion of contract budget — number only | Target gross margin % (number, e.g. 35 for 35%) | Fixed / T&M / Cost-Plus / GMP | Active / On Hold / Closed | Win probability % for Opportunities (e.g. 75) | Opportunity pipeline stage (e.g. Prospecting, Awarded) | Top-level business unit (e.g. Buildings, Infrastructure) | Your internal division managing this project | Your internal department | Project sector / industry (e.g. Healthcare, Transportation) | YYYY-MM-DD — project target start | YYYY-MM-DD — project target completion | YYYY-MM-DD — actual start date | YYYY-MM-DD — actual completion date | YYYY-MM-DD — desired completion date (optional) | YYYY-MM-DD — proposal submission deadline (optional) | YYYY-MM-DD — bid submission deadline (Opportunities) | YYYY-MM-DD — interview / shortlist date (Opportunities) | YYYY-MM-DD — preconstruction phase start (optional) | YYYY-MM-DD — preconstruction phase end (optional) | YYYY-MM-DD — actual construction start (optional) | YYYY-MM-DD — estimated construction start (optional) | YYYY-MM-DD — estimated construction end (optional) | YYYY-MM-DD — start of closeout phase (optional) | YYYY-MM-DD — project closeout / handover date (optional) | YYYY-MM-DD — date the record was fully closed (optional) | Client point of contact name for this project (optional) | Login Email or Full Name of Project Lead from your firm | Login Email or Full Name of Project Manager | Login Email or Full Name of Senior Project Manager (optional) | Login Email or Full Name of Business Lead / Principal (optional) | Login Email or Full Name of record owner (optional) | Login Email or Full Name of Program Manager (optional) | Login Email or Full Name of Lead Estimator (optional) | Login Email or Full Name of Lead Superintendent (optional) | Login Email or Full Name of Estimator (optional) | Brief project description or scope summary (optional) | Upcoming task or milestone (optional) | Next key milestone name (optional) | Risk score 1–100 (optional) | Internal priority rank (number, optional) | Abbreviated project name for dashboards (optional) | Leave blank if entering team in a separate upload | Login Email of team member assigned to this project row | Role this person plays on the project | Division for the assignment | YYYY-MM-DD — assignment start | YYYY-MM-DD — assignment end | Percentage 0–100 | Planned hours for this person on this project | Hard (confirmed) or Soft (tentative)
Project | Metro Transit Authority | David Park | Sarah Mitchell | Good | Transportation | Downtown Rail Extension — Phase 2 | JOB-2024-0412 | New Construction | Engineering | Infrastructure | Transit | Rail | 38500000 | 38500000 | 40000000 | 18200000 | 31 | Fixed | Active |  |  | Infrastructure | Civil Infrastructure | Transportation Engineering | Transportation | 2024-03-01 | 2026-08-31 | 2024-03-15 |  | 2026-07-31 | 2023-11-15 |  |  | 2024-01-10 | 2024-02-28 | 2024-03-15 | 2024-03-01 | 2026-06-30 | 2026-07-01 | 2026-08-31 |  | David Park | james.norton@aceco.com | lisa.chen@aceco.com |  | marcus.bell@aceco.com | marcus.bell@aceco.com |  |  | chris.varela@aceco.com |  | Extension of existing downtown light rail system with two new stations and 4.2km of track. | Foundation inspection | Station A structural complete | 42 | 1 | DTR-P2 |  | james.norton@aceco.com | Principal | Civil Infrastructure | 2024-03-01 | 2026-08-31 | 25 | 1200 | Hard
Project | Lakeside Medical Center | Angela Torres | Rachel Kim | Good | Healthcare | Surgical Wing Expansion | JOB-2024-0530 | Renovation | Architecture | Healthcare Facilities | Medical | Surgical | 22100000 | 22100000 | 23000000 | 9800000 | 34 | Design-Build | Active |  |  | Buildings | Healthcare Buildings | Medical Facilities | Healthcare | 2024-06-01 | 2025-11-30 | 2024-06-15 |  | 2025-10-31 | 2024-02-01 |  |  | 2024-04-01 | 2024-05-31 | 2024-06-15 | 2024-06-01 | 2025-10-31 | 2025-11-01 | 2025-11-30 |  | Angela Torres | priya.sharma@aceco.com | kevin.lau@aceco.com | lisa.chen@aceco.com | marcus.bell@aceco.com |  |  | tom.harris@aceco.com |  | tom.harris@aceco.com | Addition of a 12-OR surgical wing to the existing hospital, including new sterile processing and NICU. | MEP rough-in inspection | OR shell complete | 28 | 2 | SWX |  | priya.sharma@aceco.com | Project Manager | Healthcare Buildings | 2024-06-01 | 2025-11-30 | 100 | 3200 | Hard
Project | City of Riverside | Martin Reyes | Sarah Mitchell | Fair | Government | Riverside Civic Centre Renovation | JOB-2023-1104 | Renovation | Engineering | Government | Civic | Civic | 14750000 | 14750000 | 15000000 | 7200000 | 28 | T&M | Active |  |  | Buildings | Civic Buildings | Structural Engineering | Government | 2023-09-01 | 2025-03-31 | 2023-09-15 |  | 2025-02-28 | 2023-05-01 |  |  | 2023-07-01 | 2023-08-31 | 2023-09-15 | 2023-09-01 | 2025-02-28 | 2025-03-01 | 2025-03-31 |  | Martin Reyes | james.norton@aceco.com | priya.sharma@aceco.com | [7 empty] | Full interior renovation of the 1970s civic centre including structural upgrades, new MEP systems, and accessibility improvements. | Council chambers handover | Level 2 complete | 55 | 3 | RCC |  | james.norton@aceco.com | Principal | Civic Buildings | 2023-09-01 | 2025-03-31 | 20 | 640 | Hard
Project | Harborview Development Corp | Kevin Lau | Rachel Kim | Good | Real Estate | Harborview Mixed-Use Tower | JOB-2023-0210 | New Construction | Architecture | Commercial | Mixed-Use | Tower | 87000000 | 87000000 | 90000000 | 34000000 | 36 | Fixed | Active |  |  | Buildings | Commercial Buildings | High-Rise | Real Estate | 2023-05-01 | 2026-12-31 | 2023-05-20 |  | 2026-11-30 | 2022-12-01 |  |  | 2023-01-01 | 2023-04-30 | 2023-05-20 | 2023-05-01 | 2026-10-31 | 2026-11-01 | 2026-12-31 |  | Kevin Lau | marcus.bell@aceco.com | priya.sharma@aceco.com | lisa.chen@aceco.com | marcus.bell@aceco.com | marcus.bell@aceco.com | james.norton@aceco.com | tom.harris@aceco.com | chris.varela@aceco.com | tom.harris@aceco.com | 42-storey mixed-use tower with retail podium, 380 residential units, and rooftop amenities. | Floor 18 pour | Podium structure complete | 33 | 4 | HMT |  | marcus.bell@aceco.com | Business Lead | Commercial Buildings | 2023-05-01 | 2026-12-31 | 20 | 1440 | Hard
Opportunity | State Dept of Transport | Michelle Okonkwo | Sarah Mitchell | Good | Government | Highway 9 Bridge Replacement | JOB-2023-0880 | New Construction | Engineering | Infrastructure | Bridges | Bridge |  | 48200000 |  | 19700000 | 32 | Design-Build | Active | 65 | Shortlisted | Infrastructure | Civil Infrastructure | Bridge Engineering | Transportation | 2024-09-01 | 2027-06-30 |  |  | 2027-05-31 | 2024-04-15 | 2024-04-15 | 2024-05-10 |  |  |  | 2025-01-01 | 2027-04-30 | 2027-05-01 | 2027-06-30 |  | Michelle Okonkwo | james.norton@aceco.com | priya.sharma@aceco.com |  | marcus.bell@aceco.com |  |  | tom.harris@aceco.com |  | tom.harris@aceco.com | Full replacement of the aging Highway 9 bridge over the Riverside river, including approach roads and drainage. | Technical proposal review | Award decision | 68 | 5 | HWY9 |  | james.norton@aceco.com | Principal | Civil Infrastructure | 2024-09-01 | 2027-06-30 | 15 | 720 | Soft
Opportunity | Nexus Data Solutions | Irene Yap | Rachel Kim | Good | Technology | Tier-4 Data Centre Build | JOB-2025-0315 | New Construction | Engineering | Commercial | Data Centre | Hyperscale |  | 56000000 |  | 21500000 | 30 | GMP | Active | 40 | Prospecting | Infrastructure | MEP Infrastructure | Electrical Engineering | Technology | 2025-07-01 | 2027-09-30 |  |  | 2027-08-31 | 2025-03-01 | 2025-03-01 | 2025-04-15 |  |  |  | 2025-10-01 | 2027-07-31 | 2027-08-01 | 2027-09-30 |  | Irene Yap | marcus.bell@aceco.com | kevin.lau@aceco.com |  | marcus.bell@aceco.com |  |  | tom.harris@aceco.com |  | tom.harris@aceco.com | Greenfield Tier-4 data centre with N+1 redundancy, 32MW IT load, and on-site backup generation. | RFP response | Shortlist notification | 72 | 6 | NDC